Event Safety Management & Operations Plan

*How to use this event operations plan template*

As an event organiser, you are responsible for planning and managing risk at your event. This event operations plan template is provided by Whakatane District Council to assist you to plan and deliver a safe, healthy and operationally successful event and will compliment your other plans for programming, marketing, funding etc. This will be an evolving document that will be used to explain the operations involved in your event.

The template has been developed to reflect Whakatane District Council’s expectations for the management of risk at events and should be populated in consultation with Whakatane District Council’s event safety guidelines.

This template suggests format, wording and content tailored to your event scale, nature and complexity as described in your event application form. You are responsible for identifying additional content, editing wording to reflect your management approach and adding any and all information critical to your event operations under the Health and Safety at Work Act 2015 (HSWA).

**Notes before you start:**

This template is a suggested tool for your reference and use, reflecting Whakatane District Council’s expectations of an event operations plan. You are welcome to develop your own documentation should you choose not to use this template.

The event safety guide should be used as a reference point on the level and type of information required within this or any other health and safety documentation.

Grey text indicates where specific event information must be tailored.

Sample information is placed throughout the template for reference only and should be deleted and replaced with information specific to your event.

Sections 1 – 6 ask for operational information that describe your event and demonstrate in a general sense how you are going to deliver a safe event environment.

Section 7 suggests headings and content for more detailed plans or procedures for managing risks identified through your risk control planning (Section 6).

Section 8 provides example appendices i.e. forms, definitions and a sample risk management framework relevant to your event.

**Any questions or concerns please contact the Reserves and Bookings Administrator at Whakatane District Council. Happy planning.**

Contents

[1 EVENT HEALTH AND SAFETY COMMITMENT 5](#_Toc21686584)

[2 EVENT DETAILS 6](#_Toc21686585)

[*2.1* *Ticketing* 7](#_Toc21686586)

[*2.2* *Site map* 7](#_Toc21686587)

[*2.3* *Event programme* 8](#_Toc21686588)

[*2.4* *Production schedule and run sheet* 8](#_Toc21686589)

[4 CONTRACTOR MANAGEMENT 10](#_Toc21686590)

[*4.1* *Event Organiser Contractor Responsibilities* 10](#_Toc21686591)

[*4.2* *Contractor responsibilities* 10](#_Toc21686592)

[*4.3* *Contractor list* 10](#_Toc21686593)

[5 INDUCTIONS 12](#_Toc21686594)

[*6.1* *Risk Management Plan* 13](#_Toc21686595)

[*6.2* *Command, Control and Communication* 13](#_Toc21686596)

[*6.3* *Event day reporting and incident management* 14](#_Toc21686597)

[7 RISK CONTROL PLAN DETAILS AND SUPPORTING OPERATIONAL DOCUMENTATION 16](#_Toc21686598)

[*7.1* *Emergency Services* 16](#_Toc21686599)

[*7.2* *First Aid Provision* 16](#_Toc21686600)

[*7.3* *Notifiable Accidents Reporting Procedure (WorkSafe)* 16](#_Toc21686601)

[*7.4* *Lost Child Procedure* 18](#_Toc21686602)

[*7.5* *Security* 20](#_Toc21686603)

[*7.6* *Crowd Management* 20](#_Toc21686604)

[*7.7* *Emergency Access* 20](#_Toc21686605)

[*7.8* *Evacuation Plan* 20](#_Toc21686606)

[*7.9* *Accreditation* 20](#_Toc21686607)

[*7.10 Special Effects & Pyrotechnics* 21](#_Toc21686608)

[*7.11 Event Waste* 21](#_Toc21686609)

[*7.12 Noise* 21](#_Toc21686610)

[*7.13 Volunteers* 21](#_Toc21686611)

[*7.14 Alcohol Management* 21](#_Toc21686612)

[*7.15 Traffic And Transport* 22](#_Toc21686613)

[*7.17 Amusement Devices* 23](#_Toc21686614)

[*7.18 Power* 23](#_Toc21686615)

[*7.19 Lighting* 23](#_Toc21686616)

[*7.20 Marquees* 24](#_Toc21686617)

[*7.21 Fencing* 24](#_Toc21686618)

[*7.22 Sound/Av* 24](#_Toc21686619)

[*7.23 Staging* 24](#_Toc21686620)

[*7.24 Food Vendors* 24](#_Toc21686621)

[*7.25 Radio Communications (RTS)* 25](#_Toc21686622)

[*7.26 Information Tent* 25](#_Toc21686623)

[*7.27 Accessibility* 25](#_Toc21686624)

INSERT YOUR EVENT NAME Safety Management and Operations Plan

**Purpose**

This document outlines how ORGANISATION NAME OR INDIVIDUAL’S NAME plans to take all practicable steps to deliver a safe and therefore enjoyable event experience at EVENT NAME, DATE AND LOCATION.

We/I understand and accept that under the Health and Safety at Work Act 2015 (HSWA), We/I have at all times a duty of care to ensure the health and safety of all event participants and spectators, including event staff, contractors, subcontractors, volunteers, other event delivery participants such as sponsors, and any persons legally entitled to be at or in the vicinity of the event site.

|  |  |
| --- | --- |
| Name: |  |
| Role: |  |
| Date: |  |
| Signature: |  |

# 1 EVENT HEALTH AND SAFETY COMMITMENT

As the event organiser for EVENT NAME I/we will deliver a safe and healthy event environment for all people associated with the event, and anyone who may be affected by our activities. We will deliver this by:

1. Having a risk management process in place for identifying, documenting, assessing, managing, and reviewing event risks;
2. Providing event health and safety information to all event stakeholders through pre- planning meetings, site inductions, event signage, event day briefings and event day incident reporting;
3. Having clear health and safety roles and responsibilities for the event’s delivery team (including contractors, volunteers, delivery partners);
4. Having clear lines of communication and consultation with contractors (PCBUs1)
5. Having an agreed process for reporting and investigating incidents;
6. Conducting event day site checks and monitoring, that feeds into daily/end of event debriefs to ensure continuous improvement; and
7. Complying with all relevant legislation, regulations, codes of practice and industry standards.

1 PCBU – Person conducting a business or undertaking ref Health and Safety at Work Act 2015

# 2 EVENT DETAILS

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Event name |  | | | | | | | | | |
| Event location |  | | | | | | | | | |
| Brief description of event |  | | | | | | | | | |
|  |  | | | | | | | | | |
| Total Anticipated crowd numbers | | | |  | Spectators |  | Participants | | |  |
|  | | | | | | | | | | |
| Pack in date | |  | |  | Times |  | | to |  | |
| Event date | |  | |  |  |  | | to |  | |
| Pack out date | |  | |  |  |  | | to |  | |
|  | | | | | | | | | | |
| **KEY PERSONNEL** | | | | | | | | | | |
| Event organiser: | |  | | | | | | | | |
| Mobile number: | |  | |  | Email address: |  | | | | |
| Alternate contact: | |  | | | | | | | | |
| Mobile number: | |  | |  | Email address: |  | | | | |
| Safety co-ordinator: | |  | | | | | | | | |
| Mobile number: | |  | |  | Email address: |  | | | | |
| First aid co-ordinator: | |  | | | | | | | | |
| Mobile number: | |  | |  | Email address: |  | | | | |
|  | |  | | | | | | | | |
|  | |  | |  |  |  | | | | |
|  | | | | | | | | | | |
|  | | |  | | | | | | | |
|  | | |  | | | | | | | |

|  |  |  |  |
| --- | --- | --- | --- |
| **Key event features detailed in this plan** | **Yes** | **No** | **Notes** |
| Amusement Devices |  |  |  |
| Accessibility needs |  |  |  |
| Working at heights |  |  |  |
| Presence of alcohol |  |  |  |
| Involvement of children and/or vulnerable persons |  |  |  |
| Involvement of animals |  |  |  |
| Traffic management |  |  |  |
| Vehicles e.g. parade, vehicle access |  |  |  |
| Special effects & use of pyrotechnics/fireworks |  |  |  |
| Lasers and lighting |  |  |  |
| Smoke machines or strobe lighting |  |  |  |
| Naked flames |  |  |  |
| Noise (e.g. drumming, amplified noise) |  |  |  |
| Drones/UVAs |  |  |  |
| Temporary structures (e.g. scaffolding, stages, marquees etc.) |  |  |  |
| Ground penetration (e.g. pegging marquee or structures) |  |  |  |
| Usage of liquefied petroleum gas (LPG) (e.g. food stalls) |  |  |  |
| Electrical installations/generators |  |  |  |
| Maritime event/water involved |  |  |  |
| INSERT OTHER |  |  |  |

## *2.1 Ticketing*

INSERT DETAILS OR DELETE IF NOT RELEVANT e.g. Tickets available from: LOCATION/WEBSITE

Cost of tickets: etc.

## *2.2 Site map*

INSERT/ATTACH SITE MAP

## *2.3 Event programme*

INSERT PROGRAMME OR PROVIDE GENERAL OVERVIEW OF TYPE OF ENTERTAINMENT IF NOT FINALISED

## *2.4 Production schedule and run sheet*

INSERT (WHEN AVAILABLE) – schedule including pack in and out activities.

3 KEY CONTACTS AND RESPONSIBILITIES

The key contacts and their role/service are as follows. (After-hours contacts are required in case of an incident that needs to be communicated i.e. postponement.)

|  |  |  |  |
| --- | --- | --- | --- |
| **Responsibility** | **Name of contact** | **Contact number (during event and after hours)** | **Company/organisation** |
| Event controller/manager (24/7) |  |  |  |
| 2IC event manager (24/7) |  |  |  |
| Event H&S representative  (prior/during and post) |  |  |  |
| Liquor licensee |  |  |  |
| Stallholder manager |  |  |  |
| Event day operations centre |  |  |  |
| First aid on site |  |  |  |
| Event medical assistance provider |  |  |  |
| Local hospital/A&E |  |  |  |
| Local after hours medical centre |  |  |  |
| NZ Police (local station or officer in  charge) |  |  |  |
| Security manager |  |  |  |
| Traffic management (incl. parking) |  |  |  |
| Maritime/water safety |  |  |  |
| Waste management |  |  |  |
| Lost children |  |  |  |
| Council contact |  |  |  |
| After hours Council contact |  |  |  |
|  |  |  |  |
| INSERT OTHERS |  |  |  |

# 4 CONTRACTOR MANAGEMENT

The event recognises that contractors and the event management company are both PCBU’s (person conducting a business or undertaking) under the HSWA.

## *4.1 Event Organiser Contractor Responsibilities*

EVENT ORGANISER commits to undertaking the following actions at EVENT NAME to support delivery of a safe event environment; or where harm occurs, effective management of the occurring incident by:

* Reviewing all contractors’ event specific health and safety management plans prior to any works taking place and accepting the level of risk management associated with their works
* Site inductions for all contractors including event overview, on site hazards, H&S reporting and investigation processes, location of facilities (toilets, water) (refer to induction check list)

EVENT ORGANISER will monitor contractors when on site and will provide post event feedback to inform future planning and documentation.

## *4.2 Contractor responsibilities*

To support the delivery of a safe and successful event environment and to meet current legislation EVENT NAME/ORGANISER requires contractors to complete event specific H&S documentation; or where harm occurs, effective management of the incident, evidenced as follows:

* All contractors to follow best practice systems and processes in accordance with respective industry standards at all times
* Risk created by work undertaken by a contractor (or a subcontractor) is clearly identified, documented and managed by the contractor and communicated to the event manager/event H&S representative
* Event reporting and communication lines are followed if an incident occurs (including hazard, accidents and near misses); and
* Compliance with all required legislation and regulations.

## *4.3 Contractor list*

The following contractors have been engaged for the event.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Type of service** | **Contractor/Organisation** | **Description of services** | Contact number and email | **Event**  **specific safety plan received** | Event site induction completed/date |
| Amusement equipment |  |  |  |  |  |
| Electrical |  |  |  |  |  |
| Food stalls |  |  |  |  |  |
| Pyrotechnics |  |  |  |  |  |
| Scaffolding |  |  |  |  |  |
| Stage |  |  |  |  |  |
| Sound |  |  |  |  |  |
| Marquee |  |  |  |  |  |
| Fencing |  |  |  |  |  |
| Security |  |  |  |  |  |
| Traffic management |  |  |  |  |  |
| LP Gas |  |  |  |  |  |
| Cleaning |  |  |  |  |  |
| Waste |  |  |  |  |  |
| Drinking water |  |  |  |  |  |
| Toilet facilities |  |  |  |  |  |
| Special effects |  |  |  |  |  |
| LIST OTHER |  |  |  |  |  |
|  |  |  |  |  |  |

# 5 INDUCTIONS

EVENT ORGANISER will provide pre-briefings and onsite inductions to the above contractors to ensure H&S information is clearly communicated. (Refer induction check list in appendices for what is covered and who has been inducted on site).

|  |  |  |  |
| --- | --- | --- | --- |
| **What** | **Attendees**  Should include anyone required on site throughout pack in/pack out other than general public on event day. | **Date /time** | **Meeting location point** |
| Pre-briefing |  |  |  |
| Site induction |  | Upon arrival to site |  |

6 Risk Management

To plan for a safe and successful event and meet health and safety duties, risks that arise from the event must be effectively managed. As the event organiser we are aware that risks to health and safety arise from people being exposed to hazards.

Hazard = anything that could cause harm,

Risk = the potential harm caused by the hazard.

The risk control plan describes:


* All known event risks including during pack in and out,
* How they are being managed (eliminated or minimised),
* Who is responsible for managing the risk, and
* How it is used as a daily hazard check list.

## *6.1 Risk Management Plan*

Please refer to appendices – risk management plan template

## *6.2 Command, Control and Communication*

The below personnel chart shows the event structure and who will communicate with whom in the case of an incident, where 111 is not the first point of call. (SAMPLE: Delete and develop your own if the below is not relevant to your event.



In the case of an incident all event stakeholders are briefed to meet at INSERT LOCATION to get a detailed report on the incident, and develop the action plan to manage safety of those on site.

**Communication channels** (SAMPLE. Describe how stakeholders on site are to communicate with each other)

|  |  |  |
| --- | --- | --- |
| NZ Police | Police RT system | Site phone if relevant/mobile |
| First aid provider | Own RT system | Site phone if relevant/mobile |
| Security | Own RT system | Site phone if relevant/mobile |
| Event manager | Event RT system | Site phone if relevant/mobile |

## *6.3 Event day reporting and incident management*


The below section outlines how event day reporting will be managed depending on the incident that has occurred.

The event day log will record all key event information (weather, crowd levels, and operational issues) and incidents/accidents/near misses (minor or major).

Serious harm accidents will be noted in the event day log (see appendices). The investigation and reporting will follow WorkSafe procedures and forms (refer to risk control plan documents section titled notifiable accident reporting).

**6.3.1 Event day incident procedure**

(SAMPLE: Delete and develop your own if the below is not relevant to your event.)



**6.3.2 Emergency management**

In the case of a civil defence or emergency outside the event site/organisers control, the event will follow the instructions of the lead emergency agency (NZ Police/Fire Service). The event evacuation plan will be implemented if required, and event day incident procedure (as above) followed.

# 7 RISK CONTROL PLAN DETAILS AND SUPPORTING OPERATIONAL DOCUMENTATION

The below plans/procedures describe actions undertaken to eliminate or minimise the risks identified in the risk control plan (Section 6.1)

DELETE ANY OF THE HEADINGS IN SECTION 7 THAT DO NOT APPLY TO YOUR EVENT AND ADD ANY SPECIFIC TO YOUR RISK CONTROL PLANS.

## *7.1 Emergency Services*

NZ Police – Describe how you have engaged with Police, if they will be present at the event, key contact and onsite location.

NZ Fire Service – Describe how you have engaged with Fire Service, if they will be present at the event, key contact and onsite location.

## *7.2 First Aid Provision*

The following first aid provisions are in place:

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Describe**  **services/provider** | **Services location onsite**  **and duration** | **Contact name/mobile**  **number/radio channel** |
| Pack in | First aid kit |  |  |
| Event day |  |  |  |
| Pack out |  |  |  |

First aid register – refer to appendices.

## *7.3 Notifiable Accidents Reporting Procedure (WorkSafe)*

The event site is a workplace. Any incident that occurs within the event footprint or area of control will follow the below WorkSafe procedures.

Source: <http://www.business.govt.nz/worksafe/tools-resources>

**7.3.1 Reporting notifiable events** to WorkSafe New Zealand and key stakeholders (i.e. the land owner e.g.: local Council)

Notification to WorkSafe and any land owners (e.g. Council) will be done if a work-related event (notifiable event) occurs.

**Under HSWA, the event organiser is required to:**

* Notify WorkSafe as soon as possible, when a notifiable event occurs.
* Preserve the site of the incident until a WorkSafe inspector arrives, or you are otherwise directed.
* Keep records of all notifiable events.

**A notifiable event is a:**

* Death,
* Notifiable illness or injury, or
* Notifiable incident occurring as a result of work.

Only serious events are intended to be notified.

**Use the WorkSafe tool to assess if required:** [http://www.business.govt.nz/worksafe/notifications-forms/notifiable-events/notifiable-event- problem-solver](http://www.business.govt.nz/worksafe/notifications-forms/notifiable-events/notifiable-event-problem-solver)

**7.3.2 Notifiable event procedure**

**7.3.2.1 Preserve the site**

The person who manages or controls the event site (workplace) must take all reasonable steps to ensure that the site of the notifiable event is preserved and not disturbed until a WorkSafe inspector authorises you to do so.

**The site may only be disturbed if:**

* You need to assist the injured person,
* It's essential to make the site safe or minimise the risk of someone else being hurt or killed,
* Directed to do so by the Police, and/or
* Permitted by WorkSafe.

**To ensure the site is not disturbed:**

* The work set-up should not be changed,
* Any plant, substances or other things involved in the event should stay where they are,
* Work that could interfere with the site should stop; work may continue in other parts of the workplace, and/or
* No alterations should be made to the plant, vehicles, or structures involved.

**Note:**

If you are reporting a hazardous substances emergency, please call 111 and request New Zealand Fire Service and then the WorkSafe response team directly on 0800 030 040.

**7.3.2.2 Notify WorkSafe**

**If someone is seriously injured as a result of the event activity, then the process will be:**

* Notify WorkSafe as soon as the event organiser (or representative) is aware that someone has been seriously injured (notifiable).
* The notification will be made even if emergency services attend.
* Only one notification is required for each notifiable event.

If there are multiple businesses involved with the work, then one of the businesses/contractors will be nominated to notify WorkSafe.

Note: that all businesses involved with the work are responsible for making sure that the notification is made by the nominated business.

How to notify WorkSafe:

1. Phone: 0800 030 040

2. Online: <http://forms.worksafe.govt.nz/notifiable-event-notification>

3. Form: Refer to appendices

**7.3.2.3. Keep records**

Records of all notifiable events will be kept for at least five years from the date of the event. (Refer to forms section in appendices)

## *7.4 Lost Child Procedure*

**Lost children management plan**

Where the presence of children (or vulnerable persons) is involved, a procedure is in place to ensure the safe and timely return of lost dependents. Refer to forms section of the appendices for the lost child form.

**Lost child centre**

DESCRIBE THE AREA, LOCATION, and TYPE OF STRUCTURE AND HOW IT WILL BE IDENTIFIED TO THE PUBLIC e.g.: Tent, signposted, noted on maps and publicised via PA announcements as the location for care-givers to report or collect lost children.

**Communication**

DESCRIBE HOW EVENT STAFF AND VOLUNTEERS WILL FACILITATE COMMUNICATION FOR LOST CHILDREN e.g. all event staff, volunteers and security to have cell phones or some other form of communication device to facilitate communication re lost children.

DESCRIBE HOW YOU WILL HAVE INFORMED STAFF ON WHAT TO DO e.g. all staff briefed to take any lost children to lost child centre and on lost child procedure, contact phone number to be displayed at stage.

**Staffing**

INSERT DETAILS ON WHO WILL MANAGE THE LOST CHILD CENTRE AND PROCEDURE, HOW HAVE THEY BEEN SELECTED, HOW AND WHEN STAFF WILL BE BRIEFED ON LOST CHILD PROCEDURE e.g. procedure included in all staff briefing, hard copy of the lost child procedure is available for easy reference, staffed with 'children orientated' volunteers with childcare experience

* Minimum 2 volunteers available to staff lost child centre at all times
* One volunteer responsible for coordinating the procedure and capturing dependent’s information and another caring for the dependent/s.

**Procedure**

DESCRIBE HOW THE PROCEDURE WILL BE MANAGED FOR LOST CHILDREN e.g. the lost child centre will be the main point for coordination and collection. All staff will be briefed on the following procedure:

1. If approached by someone who has lost a child, staff will ask the following (form provided in appendices):

1. ID of the person
2. Description – sex, age, ethnic group, hair colour, clothing description, name (and if the child knows their name).
3. Location last seen/found
4. Approximate time missing/lost

2. Contact the lost child centre with details. If lost child centre cannot be contacted, contact the Event organiser.

3. Children found by staff or by a third party to be taken to the lost child centre by the staff member who finds or receives the child. Do not let the dependent go with another member of the public to the lost child centre.

4. The lost child is looked after by Lost child centre staff, who add details (a,b,c above) to register

5. Lost child centre to confirm details over radio/mobile with event staff and arrange an announcement on stage or over PA to be repeated every 10 minutes until the child is found. NO NAMES TO BE USED only a description of the child.

6. If after 30 minutes the child hasn’t been located, ensure the Police are contacted via the onsite Police if available or through the local Police Station.

7. When the dependent is found the lost child centre should ensure all staff are aware of the missing child e.g. stage manager and Police are notified and to stop the search.

8. Staff at lost child centre to ensure correct person collects dependent.

* Children are not to be given to any caregiver unless staff are satisfied with identification of the caregiver and the reaction of the dependent. Get them to sign for the dependent and print name and contact number on the lost child form (ID REQUIRED) See forms appendix.
* Check child’s reaction. If child becomes distressed or seemingly fearful staff MUST contact Police and pass on your concerns.

9. At the end of the event, if children are still present, Police to assist in repatriation.

## *7.5 Security*

Security Contractors: COMPANY NAME (refer to key contracts for details) Security base: DESCRIBE LOCATION WITHIN THE SITE

High level security schedule (refer to plan for detail)

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Date & Time**  **to – from** | **Roll** | **Key onsite**  **contact/mobile** |
| Pack in |  | Asset protection |  |
| Event |  |  |  |
| Pack out |  |  |  |

DELETE IF NOT APPLICABLE - The security plan has been reviewed by the Whakatane Police Department. INSERT/ATTACH SECURITY PLAN

## *7.6 Crowd Management*

DESCRIBE ANTICIPATED CROWD e.g. crowd demographics, expected peak times for capacity crowds, any previous crowd issues i.e. behaviour.

DESCRIBE CROWD COMMUNICATIONS PLAN e.g. agreed messaging that will be given by the stage/security/event crew in the case of different crowd issues such as when crowd is almost at capacity and how these messages be given (loud hailers/PA system/stage mics).

DESCRIBE HOW EVACUATION COMMUNICATIONS WILL BE IMPLEMENTED I.E. LINK WITH EVACUTATION PLAN.

## *7.7 Emergency Access*

The site will be set up to ensure that there are no restrictions for emergency service vehicles or personnel.

A minimum of 3 meters will be maintained along site access points and pathway/roads to allow for Fire Service and Ambulance access.

## *7.8 Evacuation Plan*

If an incident occurs that is significant, the evacuation of the event site will be agreed between the event manager, event H&S and Police/security refer to event day incident procedure section 6.

INSERT VENUE EVACUATION PLAN – SITE MAP WITH EGRESS POINTS, CROWD FLOWS, MUSTER POINT AND AN OVERVEIW ON HOW THIS WILL BE MANAGED AND COMMUNICATED.

## *7.9 Accreditation*

DESCRIBE WHO WILL RECEIVE ACCREDITION AND HOW AND WHEN THIS WILL BE DISTRIBUTED, INSERT IMAGE/S OF ACCREDITATION AND INSERT/ATTACH ACCREDITATION MAP (WHAT PASS GETS YOU WHERE)

## *7.10 Special Effects & Pyrotechnics*

Contractor name: INSERT NAME

Description of activity: DESCRIBE

Location of activity/exclusion zone: MAP

Schedule of activity pack in/event/out: DESCRIBE

Certification/license number INSERT APPROVED HANDLER, TEST DISPLAY LICENSE NUMBER

INSERT PLAN and Event/Site specific safety plan

## *7.11 Event Waste*

Waste management provider: INSERT NAME

Portaloo provider: INSERT NAME

WASTE MANAGEMENT & MINIMISATION PLAN: provide a waste management and minimization plan by completing Council’s template.

TOILET FACILITIES/PORTALOOS: OUTLINE what services are being provided, when, servicing schedule, waste incident response procedure.

## *7.12 Noise*

DESCRIBE HOW THE EVENT WILL MANAGE NOISE LEVELS/RESTRICTIONS i.e. monitoring at sound desk, comment on any decibel levels that may apply to the event location or resource consent conditions, describe any personal protective equipment required by event crew/contractors and who is providing and monitoring use.

## *7.13 Volunteers*

DESCRIBE HOW YOU WILL MANAGE VOLUNTEERS

e.g. Volunteer manager: NAME

Volunteer meeting point/rest area: location

Volunteers will have information on the event, their roles and H&S communicated by:

* a pre-briefing DATE/LOCATION (and hard copies of event documentation where required is provided) specific to their role, in addition to the pre-briefing information given to all contractors/services delivering to the event as mentioned above.
* Be inducted to site as per site induction checklist
* Recorded on the Volunteer event day check in/out sheet (refer forms).

## *7.14 Alcohol Management*

DESCRIBE ALCOHOL MANAGEMENT APPROACH

Is alcohol being allowed, supplied or sold and if so who is supplying when, license number, who has approved this and under what terms e.g. alcohol will be managed in accordance with the attached alcohol management plan. This plan has been reviewed and approved by Whakatane District Council as part of our liquor licence application.

INSERT ALCOHOL MANAGEMENT PLAN IN APPENDICIES IF REQUIRED

## *7.15 Traffic And Transport*

**7.15.1 Vehicle site access**

DESCRIBE SITE ACCESS LOCATION/TIMES/ ACCREDITATION REQUIREMENTS INSERT VEHICLE ACCESS MAP

INSERT VAP IMAGE (VEHICLE ACCREDITATION PASS)

**7.15.2 Traffic Management Plan**

The event traffic management plan has been reviewed and approved by Whakatane District Council’s transport department.

Overview of traffic management: Explain why and what, and who the contractor is.

Road closures: E.g.: Smith Street (between Brown Street and White Road) from 2pm to 8pm on Saturday, 5 June 2016.

Parking restrictions: For full plan see appendices. INSERT TMP

**7.15.3 Public Transport**

DESCRIBE PUBLIC TRANSPORT PROVISIONS / OPTIONS / BUS TIMETABLE ETC

**7.15.4 Parking**

Parking is provided at:

|  |  |  |  |
| --- | --- | --- | --- |
| Who | Location | Duration (date/ time ) | Number of car parks |
| Event crew |  |  |  |
| Volunteers |  |  |  |
| Emergency services |  |  |  |
| Entertainment |  |  |  |
| Attendees (participant/spectators) |  |  |  |
| Contingency sites |  |  |  |
| Suppliers/contractors |  |  |  |

If the parking options are full, this will be communicated by the event manager by INSERT ROLE.

DESCRIBE PROCESS TO ACTIVATE CONTINGENCY SITES e.g. Contingency sites will be opened, and event crew / security will advise attendees on the ground.

INSERT RADIO / SOCIAL MEDIA OPTIONS FOR COMMUNICATION AND WHO IS ACTIONING THIS.

**7.16 Particular hazardous work**

DELETE ONE There is no known particularly hazardous work taking place at this event/the following particularly hazardous work has been advised to WorkSafe and Whakatane District Council.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Type of work** | **Location** | **Date of work** | **Key contact** | **Date submitted/approved by WorkSafe** |
|  |  |  |  |  |
|  |  |  |  |  |

## *7.17 Amusement Devices*

All mechanical devices used at the event will hold WorkSafe certification and obtain a Permit to Operate from Council.

Land-borne inflatables (bouncy castles etc.) will operate in accordance with the WorkSafe land-borne inflatable device operating requirements.

See [http://www.business.govt.nz/worksafe/information-guidance/all-guidance-items/land- borne-inflatable-device-operating-requirements/land-borne-inflatable-device-operating-requirements.pdf](http://www.business.govt.nz/worksafe/information-guidance/all-guidance-items/land-borne-inflatable-device-operating-requirements/land-borne-inflatable-device-operating-requirements.pdf)

Where required, Council will be provided with appropriate health and safety documentation for relevant amusement devices.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Company** | **Device description** | **Device serial number** | **License/certification No.** | **Specific onsite H&S requirements** |
|  |  |  |  |  |
|  |  |  |  |  |

## *7.18 Power*

Contractor: INSERT NAME

DESCRIBE SERVICES – tagged and tested, generators

## *7.19 Lighting*

Contractor: INSERT NAME

DESCRIBE SERVICES - comment on any lux levels that may apply to the event location

(resource consent conditions)

## *7.20 Marquees*

Contractor: INSERT NAME

DESCRIBE marquee dimensions, how being secured (pegging/weights). Show on site map.

## *7.21 Fencing*

Contractor: INSERT NAME

DESCRIBE SERVICES – type e.g. crowd control barriers, if using scrim banners or signage. Show on site map.

## *7.22 Sound/Av*

Contractor: INSERT NAME

DESCRIBE SERVICES/EQUIPMENT – PA, mics etc.

## *7.23 Staging*

Contractor: INSERT NAME

DESCRIBE LOCATION(S)/DIMENSIONS.

## *7.24 Food Vendors*

The following food vendors will provide the current certificate, insurances and relevant food safety documentation.

|  |  |  |  |
| --- | --- | --- | --- |
| **Company name** | **Food description** | **Food safety license/certificate no.** | **Site induction and pre- briefing (Date/time)** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

## *7.25 Radio Communications (RTS)*

Contractor:

DESCRIBE SERVICES – Quantity of RTs, delivered on DATE.

Channels: e.g. General communications 1

Stage 2

Emergency channel 3

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **RT reference**  **no.** | **Assigned to** | **Default**  **channel** | **Sign in** | **Sign out** |
| Unique RT no. | (Name/role) |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

## *7.26 Information Tent*

Location: DESCRIBE LOCATION

Staffing: DESCRIBE WHO WILL STAFF

Provides: DESCRIBE STAFF ROLES e.g. provides event programmes, lost child forms, first aid kit, lost property / found property form

Communications: e.g. RT provided channel x/landline available)

## *7.27 Accessibility*

DESCRIBE HOW YOU HAVE INTERGRATED ACCESSIBLITIY PLANNING PROVISIONS TO KEY FACILITIES FOR MOBILITY IMPAIRED e.g. toilet, venue access, sign language and parking facilities.

8 Appendices

LIST e.g.

* Risk management plan
* Forms
* Copies of event organiser/event insurance certifications, event permit, any other relevant licenses
* Contractor site specific safety plans
* Site plan