

|  |  |  |  |
| --- | --- | --- | --- |
| **PROJECT : Kopuriki Road** | | | |
| **Project Owner : NRER team** | | | |
| **Team : NRER team** | | | |
| **Interdependencies :** **Whakatāne District Recovery project plan workstreams – community, built environment, economic, WDC, BOPRC** | | | |
| **Tasks :** | **Milestone** | **Who** | **Progress** |
| Discuss with WDC/BOPRC feasibility of project and potential sources of information and potential independent consultancy’s and develop scope | EOD June 12 | Simon | Meeting set for June 12 with BOPRC. Meeting with WDC set for June 13. |
| Project development discussion | EOW June 13 | Simon, WDC, BOPRC | Completed. Scope changed to be much narrower and focused on putting in place options. This is due to BOPRC being supportive of a solution involving culvert establishment. This needs verification from WDC as to this being the best option. |
| Set meeting between WDC Roading and BOPRC rivers and drainage engineer to meet an discuss viability of culvert option | EOW June 16 or June 23 | WDC, BOPRC | Martin Taylor to set meeting appointment. Occurred but focus is on investigative options work by consultant. Need an independent report. |
| Collate and review all the facts and known state of Kopuriki road and its r/ship with Lake Aniwaniwa (work undertaken to date) | July 30 | NRER. WDC. BOPRC | Consultants providing project brief and costs/timeline which can then be assessed for acceptance to proceed to investigation. |
| Engage with key stakeholders to keep them informed | ongoing | NRER | Occurring via email and meetings (for lake Aniwaniwa) |
| Engage with key stakeholders to keep them informed | TBC | TBA/Simon |  |
| Develop a plan towards a solution once all the options are clearly understood. | September | TBA/Simon |  |
| Engage with key stakeholders to discuss what happens next | TBC | TBA/Simon |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

A1158191